## Sheet1
Module | Task Name | Start from | Responsible person | Priority | Comment
Salescom | SME BDO New Acquisition Commission from 1st Mar20 - Commission Discrepancy | 2020-08-06 | Mahmud | Finished
ESI | B2B Revenue Raw data | 2020-08-19 | Mahmud/Aminur Bhai | Finished
ESI | Q1 Monobrand Report - Monobrand ETSAF data + Band (2 Report) | 2020-08-19 | Hafiza Apu | 1st | Need followup
ESI | SME Mapping issue | 2020-07-30 | Mahmud | Finished
ESI | Report status after RA rejection proposal | 2020-08-19 | Aminur/Sahat Bhai | Finished
Salescom | Need SIM serial and MSISDN of disbursed commission | 2020-08-23 | Mahmud | Finished
ESI | B2C Retailer mapping modification | 2020-08-20 | Mehjabeen Apu | Finished
ESI | Email nofication investigation | 2020-08-19 | Aminur Bhai | Finished
ESI | Manual data calculation system input | 2020-08-19 | Aminur/Sahat Bhai | Finished
Salescom | Favicon change requirement | 2020-08-23 | Aminur Bhai/Amirul Bhai | Finished
ESI | Q3 Report query and data process | 2020-08-23 | Mahmud | 1st | Ongoing (monobrand 80%, B2B 80%) total 50%
Salescom | 4G Sim Replacement Detail | 2020-08-25 | Aminur Bhai | Finished
ESI | ESI mapping automated process creation | 2020-08-25 | Mahmud | 2nd | Need to check
ESI | Target must be uploaded after mapping upload - but they don’t maintain | 2020-09-01 | Mahmud | Finished
ESI | Target upload warning for mapping upload(gramatical error) | 2020-09-03 | Mahmud |  | Need to fix in next publish
ESI | Same DD multiple Employee | 2020-09-08 | Mahmud+Aminur Bhai | 2nd | Need to study/Talk to Amirul Bhai | meeting
ESI | Q1 SME report (Manual Data+Calculation) | 2020-09-09 | Mahmud/Aminur Bhai | Finished
ESI | Q1 2 B2B report (Manual Data+Calculation) | 2020-09-09 | Mahmud/Aminur Bhai | Finished
ESI | Q1 2 B2C Report - Lifting calculation(Done) + mapping + Band (1 Report) | 2020-09-15 | Mahmud/Mahjabeen Apu | 1st | Need to regenerate/ Need to reupload mapping
ESI | Q1 SME Report + Band (1 Report) | 2020-09-15 | Mahmud | 1st | Need to regenerate
ESI | Q1 B2B Report + Band (2 Report) | 2020-09-15 | Mahmud | 1st | Need to regenerate
ESI | Investigate Band Change effect on - Q1 report already approved by all | 2020-09-22 | Mahmud | 1st | Need to check
ESI | Prepare automation for Band change | 2020-09-22 | Mahmud | 1st | Need to check
Salescom | Need to Investigate/fix monobrand variable report | 2020-09-22 | Hafiza Apu | Finished
ESI | ESI Incentive Payout new tradition | 2020-09-20 | Mahmud | 2nd | Need to check
Salescom | Sim Replacement daily report revision | 2020-09-20 | Mahmud | Finished
ESI | ESI Monobrand Q3 decay calculation and report | 2020-09-29 | Mahmud | 1st | Need to check
ESI | ESI report view/ Dashboard view | 2020-09-29 | Mahmud | 1st | Need to check
| Scorecard/attachment show in owndashboard |  | buddin |  | Problem
| Report will include subkpi wise achievement |  |  | 1 | One Employee- one sales channel type - dashboad
| linear scale incentive payout |  |  | 2 | Month/Quarter mid change and exists both report
Role/department change effect on dashboard system
Auto Dashboard role assign for designation changes

## Mustak
Module | Task Name | Status | Start from | Responsible person | Priority | Comment | Mail Sub
SaleCom | Purgeing poeration next 18-July-21 | Panding |  | Mustak |  | discussion need with Aminur Bhai
SaleCom | MoM-Meeting on Corporate SIM replacement | No Status |  | Fida Bhai |  | Pending at Fida Bhai
SaleCom | B2B ICT Commission for BDO CAM | No Status |  | Mustak |  | Need followup Aminur Bhai
SaleCom | Temp table drop | Done |  | Mustak |  | waiting for go ahead
SaleCom | Post-Paid base push with our barrer connection (Kafi Bhai) | done |  | Masud vai |  | need to check after 2 may | B2C Postpaid Reactivation Commission
SaleCom | New NID GA and 2 column add in B2B Segment Report table | Done |  | Masud vai |  |  | Data Source for Commission/ESI of Newly Introduced KPI
SaleCom | please see this issue | Done |  |  |  | SELECT * FROM user_segments;
ESI | New developmetn plan share(detail report download) | Cancel |  |  |  |  | Details report download requirement ESI portal (Internal)
SaleCom | 30-Apr-21 B2B Segment Report data | Done |  | Masud vai |  | Next week | Data Source for Commission/ESI of Newly Introduced KPI (Internal)
SaleCom | Live Server Screenshot in 1st day of every month for CM | Panding |  | Mustak |  | take snap shot 1st day of every month | FW: Monthly IT Change Management Report: May-2021 (Internal)
SaleCom | Monthly IT Change Management Report for Live Server | Panding |  | Mustak |  | Eveery Month 9th or 10th day and take snap shot 1st day of every month | FW: Monthly IT Change Management Report: May-2021 (Internal)
SaleCom | Preper Access List for RA Team for Salecom&ESI and send to Topu Bhai | Done |  | Mustak
ESI | ESI Report Run for Q3 Arrear 3 Report | Halt |  | Mustak |  | Halt for 4G Penetration Data Q3_20
SaleCom | POS Uplod SP change and Test in Test Sertver | in progress |  | Arif Bhai |  | I done my site task, now he check his site
ESI | 4G Penetration Data Q3_20 | Halt |  | Tamim Bhai
ESI | MB Decay Data | Done |  | Hafiza Apu
ESI | MB CC dar Recharge target uplod as manual data
SaleCom | Add BLSALCOMAPP02 server to production
|  | Panding |  | Khairul Bhia |  | Daily Instant Commission gap for 4th Aug'21 | decision pending in Business end
|  | Panding |  | Fida Bhai |  | Commission for Postpaid sales through Monobrand | decision pending in Business end
|  | Panding |  | Business |  | Regarding dispute of Agnostic App Commission for Mar'21 | decision pending in Business end
|  | Panding |  |  |  | Add BLSALCOMAPP02 server to production | Waiting for Amirul bhai Approval
|  | Panding |  |  |  | Production server risk list | upgrade JQuery liberty version issue - decision pending in Faisal Bhai end

## Meeting Discussion
Meeting Date 14-Sep-21
SL | Issue | Action Point
1 | Remove msg_center files from main folder | First, we try to stop generating those log files else try to generate in a folder else manually delete those log files from the server but this is risky
2 | Sim replacement issue for 30-Aug-21 | Revision report generated and disbursed mean done.
3 | Postpaid_Deposit_DWH table start & end flag | Panding in DWH end
4 | Monobrand ESI arrear configation issue | Add validation in arrear report setup for maintaining arrear sequence e.g. arrear 2 report can not setup before arrear 1 calculation done.

## Last Puging Hisory
TABLESPACE_NAME | CURRENT_SIZE_GB | USED_SIZE_GB | FREE_SIZE_GB | FREE_STORAGE_PARCENT | OCCUPIED_STORAGE_PARCENT | DATA_SIZE_DATE
SALESCOM_INDEX_01 | 431 | 330.47 | 100.53 | 23.32 | 76.68 | 2021-03-04
SALESCOM_DATA_01 | 1380 | 1256.6 | 123.4 | 8.94 | 91.06 | 2021-03-04
TABLESPACE_NAME | CURRENT_SIZE_GB | USED_SIZE_GB | FREE_SIZE_GB | FREE_STORAGE_PARCENT | OCCUPIED_STORAGE_PARCENT | DATA_SIZE_DATE
SALESCOM_INDEX_01 | 431 | 299.45 | 131.55 | 30.52 | 69.48 | 2021-03-04
SALESCOM_DATA_01 | 1380 | 1167.99 | 212.01 | 15.36 | 84.64 | 2021-03-04
Before purging DB storage status
TABLESPACE_NAME | TOTAL | USED | FREE | PCT | DATE
SALESCOM_DATA_01 | 1520 | 1363.94 | 156.06 | 89.73 | 2021-05-18
SALESCOM_INDEX_01 | 461 | 344.35 | 116.65 | 74.7 | 2021-05-18
After purging DB storage status
SALESCOM_DATA_01 | 1520 | 1274.15 | 245.85 | 83.83 | 2021-05-18
SALESCOM_INDEX_01 | 461 | 311.79 | 149.21 | 67.63 | 2021-05-18
Total Free in GB |  | 89.79 | % | 5.9
After 399 temp table drop DB storage status
SALESCOM_DATA_01 | 1520 | 1268.42 | 251.58 | 83.45 | 2021-05-18
SALESCOM_INDEX_01 | 461 | 311.79 | 149.21 | 67.63 | 2021-05-18
Total Free in GB |  | 5.73 | % | 0.38
DB Space Status Report
TABLESPACE_NAME | TOTAL | USED | FREE | PCT | DATE
SALESCOM_DATA_01 | 1520 | 1371.71 | 148.29 | 90.24 | 2021-06-28
SALESCOM_INDEX_01 | 461 | 335.87 | 125.13 | 72.86 | 2021-06-28
Before purging DB storage status
TABLESPACE_NAME | TOTAL | USED | FREE | PCT | DATE
SALESCOM_DATA_01 | 1520 | 1461.59 | 58.41 | 96.16 | 2021-08-05
SALESCOM_INDEX_01 | 461 | 351.74 | 109.26 | 76.3 | 2021-08-05
After purging DB storage status
SALESCOM_DATA_01 | 1520 | 1333.72 | 186.28 | 87.74 | 2021-08-05
SALESCOM_INDEX_01 | 461 | 306.68 | 154.32 | 66.52 | 2021-08-05
Total Free in GB |  | 127.87 | % | 8.42
After 300 GB add DB storage status
TABLESPACE_NAME | TOTAL | USED | FREE | PCT | DATE
SALESCOM_INDEX_01 | 461 | 306.68 | 154.32 | 66.52 | 2021-08-05
SALESCOM_DATA_01 | 1820 | 1333.88 | 486.12 | 73.29 | 2021-08-05

## ESI_Q1_21_Status (hidden)
SL | Report Name | Report Status | FPnA Approval Date | Target | Mapping | Maping Upload Date | Manual Data | Manual Data Upload Date | Report Generation/IT Plan Date
1 | Q1_M3_2021 B2C (Monobrand) - Executive/Senior Executive | Pending Report Approval by RA (L1) | 2021-05-03 16:14 | Uploaded | Uploaded | 2021-05-03 16:21 | Uploaded | 2021-05-03 15:56 | 2021-05-06
2 | Q1_M3_2021 B2C (Monobrand) - Senior Manager | Pending Report Approval by RA (L1) | 2021-05-03 16:12 | Uploaded | Uploaded | 2021-05-03 16:21 | Uploaded | 2021-05-03 15:56 | 2021-05-06 15:10
3 | Q1_2021 EB (KEY) - Corporate Group Manager | Pending Report Approval by RA (L1) | 2021-05-04 11:41 | Uploaded | Uploaded | Between 03-MAY-21 00:38:27 and 05-MAY-21 02:02:04 | Uploaded | Between 05-MAY-21 02:20:18 and 05-MAY-21 06:22:17 | 2021-05-09 15:10
4 | Q1_2021 EB (KEY) - Corporate Account Manager | Pending Report Approval by RA (L1) | 2021-05-04 11:49 | Uploaded | Uploaded |  | Uploaded |  | 2021-05-09 15:10
5 | Q1_2021 EB (STRATEGIC) - Corporate Account Manager | Pending Report Processing by IT | 2021-05-04 14:42 | Uploaded | Uploaded |  | Uploaded |  | 2021-05-11 15:10
6 | Q1_2021 EB (STRATEGIC) - Corporate Group Manager | Pending Report Processing by IT | 2021-05-04 14:46 | Uploaded | Uploaded |  | Uploaded |  | 2021-05-11 15:10
7 | Q1_2021 EB (MEDIUM) - Corporate Group Manager | Pending Report Processing by IT | 2021-05-04 14:48 | Uploaded | Uploaded |  | Uploaded |  | 2021-05-11 15:10
8 | Q1_2021 EB (MEDIUM) - Corporate Account Manager | Pending Report Processing by IT | 2021-05-04 14:49 | Uploaded | Uploaded |  | Uploaded |  | 2021-05-11 15:10
9 | Q1_M3_2021 B2C (SME) - Regional SME Manager | Pending Report Processing by IT | 2021-05-06 17:16 | Uploaded | Uploaded |  | Uploaded | 2021-05-04 20:55 | 2021-05-12
10 | Q1_M3_2021 B2C (SME) - Corporate Account Manager | Pending Report Processing by IT | 2021-05-06 17:16 | Uploaded | Uploaded |  | Uploaded | 2021-05-04 20:55 | 2021-05-12
11 | Q1_M3_2021 B2C - Zonal Manager/Territory Officer | Pending Report Processing by IT | 2021-05-06 17:18 | Uploaded | Uploaded | 2021-05-05 10:06 | Uploaded | 2021-05-05 10:08

## ESI Current Status
SL | Report Name | Report Status | FPnA Approval Date | Target | Mapping | Manual Data | Report Generation/IT Plan Date
1 | Q2_2021 EB (KEY) - Corporate Group Manager | Pending Report Processing by IT | 02-Aug-21 (16:55) | Uploaded | Uploaded | Uploaded | 2021-08-11
2 | Q2_2021 EB (KEY) - Corporate Account Manager | Pending Report Processing by IT | 02-Aug-21 (16:55) | Uploaded | Uploaded | Uploaded
3 | Q2_2021 EB (MEDIUM) - Corporate Group Manager | Pending Report Processing by IT | 02-Aug-21 (17:00) | Uploaded | Uploaded | Uploaded | 2021-08-16
4 | Q2_2021 EB (MEDIUM) - Corporate Account Manager | Pending Report Processing by IT | 02-Aug-21 (17:02) | Uploaded | Uploaded | Uploaded
5 | Q2_2021 EB (STRATEGIC) - Corporate Account Manager | Pending Report Processing by IT | 02-Aug-21 (17:03) | Uploaded | Uploaded | Uploaded | 2021-08-18
6 | Q2_2021 EB (STRATEGIC) - Corporate Group Manager | Pending Report Processing by IT | 02-Aug-21 (17:05) | Uploaded | Uploaded | Uploaded
7 | Q2_2021 B2C (SME) - Corporate Account Manager | Pending Report Processing by IT | 03-Aug-21 (12:19) | Uploaded | Uploaded | Not Need | 2021-08-08
8 | Q2_2021 B2C (SME) - Regional SME Manager | Pending Report Processing by IT | 03-Aug-21 (12:21) | Uploaded | Uploaded | Not Need
9 | Q2_2021 B2C - Zonal Manager/Territory Officer | Pending Report Processing by IT | 03-Aug-21 (17:59) | Uploaded | Uploaded | Uploaded | 2021-08-09
10 | Q2_2021 B2C (Monobrand) - Executive/Senior Executive | Pending Report Processing by IT | 04-Aug-21 (21:52) | Uploaded | Uploaded | Uploaded | 2021-08-23
11 | Q2_2021 B2C (Monobrand) - Senior Manager | Pending Report Processing by IT | 04-Aug-21 (21:34) | Uploaded | Uploaded | Uploaded
12 | Q4_2020_Arrear_1 EB (MEDIUM) - Corporate Account Manager | Pending Report Processing by IT | 07-Jun-21 (12:22) | Uploaded | Previous mapping use | Not Need | 2021-08-04
13 | Q4_2020_Arrear_1 EB (MEDIUM) - Corporate Group Manager | Pending Report Processing by IT | 07-Jun-21 (12:21) | Uploaded | Previous mapping use | Not Need
14 | Q4_2020_Arrear_1 EB (KEY) - Corporate Account Manager | Pending Report Processing by IT | 07-Jun-21 (12:21) | Uploaded | Previous mapping use | Not Need
SL | Report Name | Report Status | FPnA Approval Date | Target | Mapping | Manual Data | Report Generation/IT Plan Date
1 | Q4_2020_Arrear_1 EB (KEY) - Corporate Group Manager | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded | 2021-09-06
2 | Q4_2020_Arrear_1 B2C (SME) - Corporate Account Manager | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded | 2021-09-09
3 | Q4_2020_Arrear_1 B2C (SME) - Regional SME Manager | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded
4 | Q1_M3_2021_Arrear_3 B2C (Monobrand) - Executive/Senior Executive | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded
5 | Q1_M3_2021_Arrear_3 B2C (Monobrand) - Senior Manager | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded
6 | Q1_M2_2021_Arrear_2 B2C (Monobrand) - Executive/Senior Executive | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded
7 | Q1_M2_2021_Arrear_2 B2C (Monobrand) - Senior Manager | Pending Report Processing by IT |  | Uploaded | Previous mapping use | Uploaded

## Sheet3
Current Table Structure
MSISDN | IS_MNP | SUBSCRIPTIONID | FCD | SUBSCRIPTION_TYPE | RECHARGE_PURPOSE | PURCHASE_DATE | AMOUNT | DEPOSIT_DATE | SERVICE_NUMBER | EVENT_DATE | TIME_TEXT_24 | LOAD_DATE
1674776955 | YES | 399021063 | 2021-08-16 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-16 | 500 | 2021-08-16
1714028682 | YES | 390618504 | 2021-08-31 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-31 | 350 | 2021-08-31 | Marging new table format with current structure
1911316383 | YES | 403817829 | 2021-08-10 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-10 | 649 | 2021-08-10 | SUBSCRIBER_NUMBER | DATE_VALUE | NULL | SYSDATE
1911601111 | YES | 393020392 | 2021-08-12 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-12 | 350 | 2021-08-12
1918660666 | YES | 390817823 | 2021-08-10 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-10
1914535021 | NO | 390918521 | 2021-08-10 | Retail2Postpaid | RCTK299POSTMIXBDNLOP | 2021-08-10 | 407 | 2021-08-10
1911415525 | NO | 325409666 | 2021-08-21 | Retail2Postpaid | TK5BTL7MIN6HRS | 2021-08-21 | 1100 | 2021-08-21
1911415525 | NO | 325409666 | 2021-08-21 | Retail2Postpaid | RCTK999POSTMIXBDNLOP | 2021-08-21 | 1100 | 2021-08-21
select MSISDN,SUBSCRIPTIONID,get_date(FCD) fcd,SOURCE_ID SUBSCRIPTION_TYPE ,RECHARGE_PURPOSE
,get_date(b.DATE_KEY) PURCHASE_DATE,AMOUNT,get_date(c.DATE_KEY) DEPOSIT_DATE
from
(
select MSISDN, SUBSCRIPTIONID, FCD,PRODUCT_CODE SOURCE_ID
from simrepository where FCD between 6057 and 6087
and msisdn in ('01911316383','01918660666','01911601111','01674776955','01914535021','01911415525','01714028682')
) a
left join
(
select DATE_KEY, SUBSCRIPTION_KEY, RECHARGE_PURPOSE
from bundle_recharge_com WHERE DATE_KEY between 6057 and 6087
) b on b.SUBSCRIPTION_KEY=a.SUBSCRIPTIONID and a.FCD=b.DATE_KEY
left join
(
select DATE_KEY, SUBSCRIPTION_KEY, AMOUNT
from postpaid_deposit_com where DATE_KEY between 6057 and 6087
) c on a.SUBSCRIPTIONID=c.SUBSCRIPTION_KEY and a.FCD=c.DATE_KEY